## Slide 1: Preparing your summer internship
Hot Summer/Cool Research Program
V2.0
Francisco Guzman
16- Apr-2015

## Slide 2: Our Mandate
Education
Research
Comm. Devel.
Mentor Local Students
?
Notes: We are part of the ALT group in QCRI. So Arabic is at the heart of our work (Research)
But also, one of Qatar Foundation’s main goal is Education, and we feel strongly compelled to
But also, we
We had two motivations.
We are a research institute, in our group

## Slide 3: Hot Summer -Cool Research!
ALT Started it in 2012

## Slide 4: So, you’re getting an intern…
zoitz.com

## Slide 5: The Hot Summer/Cool Research program
Intern
Gives
  Time
  Labor
What they get:
  Learn a new skill
  Practice previous skills
  Learn about research
Scientist
Gives
  Time
    Planning
    Coaching
What you get:
  Learn coaching skills
  Get some work done
  Spread the research spirit

## Slide 6: Different levels of development
1- Lack of experience, low competence, insecure
2- Some competence, ready to be developed, willing or motivated
3-Increasing competence, potentially able, not fully confident
4- High competence, high commitment, able, willing and motivated
Summer Interns
Directing
Coaching
Supporting
Delegating
Them:
You’ll be:
Post-Docs
PhD Students

## Slide 7: The typical student
May/May not have coding experience
  CMU-CS students start coding in yr1 (Python)
  Coding restricted to few class projects
  Tip: Look for hackathon participation
May/May not have design experience
  CMU-IS come stronger in this field (Web)
May/May not have research experience
  Only few have read a scientific paper
  Even fewer have technical writing skills
Adjust your expectations
Design your plan accordingly

## Slide 8: Being HSCR a coach involves…
Planning
  Breaking the the goals into bite-sized tasks
Monitoring/Mentoring
  Looking out for roadblocks
  Helping them to figure out solutions

## Slide 9: Planning
What is the goal of the project?
Which questions are going to be solved?
What needs to be done?
Who is going to do it?
When does this need to happen?
How do we know we reached the goal?

## Slide 10: 8-week program
Week | Sample task | 
Week 1 | Read and understand Current code . Investigate how it works. Propose architecture for multiplex. | 
Week 2 | Implement lightweight clients. Design proxy/handshaker | 
Week 3 | Multi plex client. Multiplex server | 
Week 4 | Integration with Session management. | 
Week 5 | Connect multiple clients + stress test. Run language classifier | 
Week 6 | Implement language classifier on test. | 
Week 7 | Implement training for language classifier on the fly | 
Week 8 | Finish Report. Peer Review colleagues reports. Prepare documentation. Prepare final presentation/poster. | 
Preparation/Warm up
Wrap up
Most of the work
Tip: Ask the students to write a small report each week. This makes it easier to write a final report

## Slide 11: Focus
Things work best if you have a final goal in mind
  A final report
  A poster for ARC is a good goal
  A workshop paper
  A small demo app
But be realistic!
  You only have 8 weeks
  Students won’t stick around after the internship
  Once school starts, it’s game over!

## Slide 12: Monitoring/Mentoring
Daily/Every-other-day quick round of advances
-any complication/problem?
Every week reality check
-are we in track?
Midterm evaluation
-report about the intern performance.
Final evaluation
-report about performance, final presentation

## Slide 13: Ideally students should be:
Involved in creative/discovery process.
Encouraged them to solve their own problems
  What is the problem?
  What are alternatives?
  What are pro’s and con’s?
  What do they think is the right path?
Own the task/project
Leave legacy, make something useful

## Slide 14: Weekly Digest
I recommend to ask the students to produce:
A small report (one page)
A small presentation (one slide)
This makes it easier to detect roadblocks/adjust planning

## Slide 15: The Process
Things don’t always work as planned
Be flexible!

## Slide 16: Dos and Don’ts
Do
Be selective
  We want to have the best students
Plan ahead
  Set goals for every week
  Be flexible
Encourage team spirit
  Set up your project for a group of two or more students
  Have interns sit together
Meet regularly with students
Don't
Allow students to part-time
  Students should be 100% committed to HSCR internship
Allow students to work from home
  Hinders team spirit
Micromanage/Be a control freak
  Let them come up with their own solutions
Leave students unattended for more than thee days
  They get lost easily
  If you need to leave, someone needs to cover

## Slide 17: Tools – What we use
Skype for communication
Dropbox for sharing documents
Github for archiving files and revision control
Trello for lightweight task management
However
There is no substitute for face-to-face time, and a good ‘ol whiteboard

## Slide 18: Thanks
Good luck in you internship projects